## DataLockup5
For OEM (junior 3D,junior prototype)
March 2022
3D average salary/month | 10159.6593
2D average salary/month | 7223.4427
Prototype average salary/month | 7481.9679
3D average salary/hour | 57.7253 |  | 51
2D average salary/hour | 41.0423 |  | none
Prototype average salary/hour | 42.5112 |  | 39
Classic | M5750 Aston Martin DB4 Zagato |  |  |  | Classic | M5768 Ford GT40 |  |  |  | Classic | M6210 Aston Martin DB5 Vintage |  |  |  | Classic | M0648 Mesarati 250F
| Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB
3D labour cost | 3000 | 1490 | 86010.7519 |  | 3D labour cost | 3000 | 2041 | 117817.4125 |  | 3D labour cost | 1800 | 1132 | 65345.0813 |  | 3D labour cost | 2000 | 1500 | 86588.0053
Prototype labour cost |  | 1373.5 | 56371.5825 |  | Prototype labour cost |  | 1167 | 47896.35 |  | Prototype labour cost |  | 699 | 28688.5593 |  | Prototype labour cost |  | 236.5 | 9706.5011
2D labour cost |  | 261 | 11095.4182 |  | 2D labour cost |  | 595 | 25294.1527 |  | 2D labour cost |  | 606 | 25761.7757 |  | 2D labour cost |  | 98 | 4166.0957
SLA (parts and jig) |  |  | 16610 |  | SLA (parts and jig) |  |  | 13080 |  | SLA (parts and jig) |  |  | 32990 |  | SLA (parts and jig) |  |  | 25245
CNC |  |  | 19000 | aluminium | CNC |  |  | 11545 | aluminium | CNC |  |  | 9550 | chemical wood | CNC |  |  | 10150
Lost Wax (brass) |  |  | 11000 | inc. mould | Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | 4200 |  | Lost Wax (brass) |  |  | n/a
PE |  |  | 4954.03 |  | PE |  |  | 7864.67 |  | PE |  |  | 3685.64 |  | PE |  |  | 2625.79
Decal @30sheets |  |  | 2840.7 |  | Decal @30sheets |  |  | 3265.5 |  | Decal @30sheets |  |  | 796.76 |  | Decal @30sheets |  |  | 1911.6
Pad Print |  |  | 1262.42 |  | Laser cutting |  |  | 524.75 |  | Laser cutting |  |  | n/a |  | Laser cutting |  |  | 100
Silk Print |  |  | n/a |  | Pad Print |  |  | 1188.16 |  | Pad Print |  |  | 74.26 |  | Pad Print |  |  | TBC
[5 empty] | Silk Print |  |  | 948.5 |  | Silk Print |  |  | n/a |  | Silk Print |  |  | TBC
|  |  | 209144.9026 |  |  |  |  | 229424.4952 |  |  |  |  | 171092.0763 |  |  |  |  | 140492.9921
GT | M6181 Ferrari 171 ( 296 GTB ) |  |  |  | GT | M6003 Mercedes AMG ONE |  |  |  | GT | M6199 Ferrari Daytona SP3 |  |  |  | GT | M6227 Ferrari 175 Purosangue
| Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB
3D labour cost | 1600 | 836.5 | 48287.2443 |  | 3D labour cost | 2600 | 1234 | 71233.0657 |  | 3D labour cost | 1800 | 792 | 45718.4668 |  | 3D labour cost | 2000 | 1379.5 | 79632.1022
Prototype labour cost |  | 946.5 | 38846.5255 |  | Prototype labour cost |  | 1600 | 65667.6607 |  | Prototype labour cost |  | 1207 | 49538.0416 |  | Prototype labour cost |  | 1190 | 48840.3227
2D labour cost |  | 124 | 5271.3864 |  | 2D labour cost |  | 288.5 | 12264.4757 |  | 2D labour cost |  | 395 | 16791.9165 |  | 2D labour cost |  | 282 | 11988.153
SLA (parts and jig) |  |  | 14990 |  | SLA (parts and jig) |  |  | 31110 |  | SLA (parts and jig) |  |  | 29458.6 |  | SLA (parts and jig) |  |  | 40790
CNC |  |  | 1200 | chemical wood | CNC |  |  | 2100 | chemical wood | CNC |  |  | 8525 | chemical wood | CNC |  |  | 13143
Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | 4000
PE |  |  | 1876.41 |  | PE |  |  | 2651.63 |  | PE |  |  | 1273.71 |  | PE |  |  | 2280.42
Decal @30sheets |  |  | 2377.5 |  | Die cutter |  |  | 176.99 |  | Laser cutting |  |  | 339.8 |  | Die cutter |  |  | 485.4
Pad Print |  |  | 892.6 |  | Decal @30sheets |  |  | 7433.4 |  | Decal @30sheets |  |  | n/a |  | Decal @30sheets |  |  | 6365.1
Silk Print |  |  | 385.14 |  | Pad Print |  |  | 891.12 |  | Pad Print |  |  | 371.3 |  | Pad Print |  |  | 864.82
[5 empty] | Silk Print |  |  | 123 |  | Silk Print |  |  | 477 |  | Silk Print |  |  | 399
|  |  | 114126.8063 |  |  |  |  | 193651.3421 |  |  |  |  | 152493.8348 |  |  |  |  | 208788.3179
F1 | M6171 Ferrari SF21 |  |  |  | F1 | M6184 RB16B Monaco |  |  |  | F1 | M6213 Ferrari F1-75 |  |  |  | F1 | M6264 Ferrari SF23
| Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB |  |  | Target Time, hr | Actual time, hr | RMB
3D labour cost | 700 | 480 | 27708.1617 |  | 3D labour cost | 700 | 488 | 28169.9644 |  | 3D labour cost | 650 | 398 | 22974.6841 |  | 3D labour cost | 800 | 392 | 22628.332
Prototype labour cost |  | 461 | 18920.4947 |  | Prototype labour cost |  | 453 | 18592.1564 |  | Prototype labour cost |  | 239 | 9809.1068 |  | Prototype labour cost |  | 237.5 | 9747.5434
2D labour cost |  | 192 | 8162.1468 |  | 2D labour cost |  | 123 | 5228.8753 |  | 2D labour cost |  | 208.5 | 8863.5812 |  | 2D labour cost |  | 215 | 9139.9039
SLA (parts and jig) |  |  | 5500 |  | SLA (parts and jig) |  |  | 5100 |  | SLA (parts and jig) |  |  | 5340 |  | SLA (parts and jig) |  |  | 5609
CNC |  |  | n/a |  | CNC |  |  | n/a |  | CNC |  |  | n/a |  | CNC |  |  | n/a
Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | n/a |  | Lost Wax (brass) |  |  | n/a
PE |  |  | 1337.32 |  | PE |  |  | 1261.03 |  | PE |  |  | 96.48 |  | PE |  |  | 779.44
Decal @30sheets |  |  | 4068.3 |  | Laser cutting |  |  | 44.55 |  | Laser cutting |  |  | n/a |  | Laser cutting |  |  | n/a
Pad Print |  |  | n/a |  | Decal @30sheets |  |  | 2301.3 |  | Decal @30sheets |  |  | 10805.1 |  | Decal @30sheets |  |  | 6106.2
Silk Print |  |  | n/a |  | Pad Print |  |  | 148.52 |  | Pad Print |  |  | 74.26 |  | Pad Print |  |  | n/a
[5 empty] | Silk Print |  |  | n/a |  | Silk Print |  |  | n/a |  | Silk Print |  |  | n/a
|  |  | 65696.4232 |  |  |  |  | 60846.3961 |  |  |  |  | 57963.2121 |  |  |  |  | 54010.4193
[10 empty] | OTHERS | M6189 SR71 Black Bird
[11 empty] | Target Time, hr | Actual time, hr | RMB
[10 empty] | 3D labour cost | 1500 | 230 | 13276.8275
[10 empty] | Prototype labour cost |  | 772 | 31684.6463
[10 empty] | 2D labour cost |  | 150 | 6376.6772
[10 empty] | SLA (parts and jig) |  |  | 56820
[10 empty] | CNC |  |  | n/a
[10 empty] | Lost Wax (brass) |  |  | n/a
[10 empty] | PE |  |  | 981.82
[10 empty] | Laser cutting |  |  | n/a
[10 empty] | Decal @30sheets |  |  | 9438
[10 empty] | Pad Print |  |  | n/a
[10 empty] | Carbon fiber tube |  |  | 282
[10 empty] | Silk Print |  |  | n/a
118859.9709
[10 empty] | OTHERS | M6199 CPO Ferrari Daytona SP3
[11 empty] | Target Time, hr | Actual time, hr | RMB
[10 empty] | 3D labour cost | 500 | 173 | 9986.4833
[10 empty] | Prototype labour cost |  | 533.5 | 21896.0606
[10 empty] | 2D labour cost |  | 22.5 | 956.5016
[10 empty] | SLA (parts and jig) |  |  | 11300
[10 empty] | CNC |  |  | 4200
[10 empty] | Lost Wax (brass) |  |  | n/a
[10 empty] | PE |  |  | 351.09
[10 empty] | Laser cutting |  |  | n/a
[10 empty] | Decal @30sheets |  |  | n/a
[10 empty] | Pad Print |  |  | 189.26
[10 empty] | Silk Print |  |  | n/a
48879.3955
Note on S66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有9台飞机的SLA,最后一台是2023-02-16

## Project cost Summary
Classic M5750 Aston Martin DB4 Zagato | Classic M5768 Ford GT40 | Classic M6210 Aston Martin DB5 Vintage | Classic M0648 Mesarati 250F
209144 | 229424 | 171092 | 140492
GT M6181 Ferrari 171 ( 296 GTB ) | GT M6003 Mercedes AMG ONE | GT M6199 Ferrari Daytona SP3 | GT M6227 Ferrari 175 Purosangue
114126 | 193651 | 152493 | 208788
F1 M6171 Ferrari SF21 | F1 M6184 RB16B Monaco | F1 M6213 Ferrari F1-75 | F1 M6264 Ferrari SF23
65696 | 60846 | 57963 | 54010
OTHERS M6189 SR71 Black Bird
118859
OTHERS M6199 CPO Ferrari Daytona SP3
48879

## DataLockup3
2023年开发已完成项目详细统计表
No | SKU |  | designer | Scale | (3D+Prototype) Planning Time | (3D+Prototype) Actual Time | 3D Actual Time | Prototype Actual Time | Start time (WK) | complete time (WK) | Remark
1 | M6202 | Mosquito / BY UK | Cary, Sheng | 1/16 | 1500 | 1720 | 1065 | 655 | WK42(2022) | WK39(2023)
2 | M6266 | Ferrari 175 Purosangue (SUV) / BY CN | sheng | 1/12 | 500 | 110 | 110 | 0 | WK45(2022) | WK50(2022) | 画了一半，已转给外面画
3 | M6199-CPO | Ferrari Daytona SP3 150 BD CPO/ BY CN | Tall Boy | 1/8 | 800 | 722.5 | 189 | 533.5 | WK25(2022) | WK31(2023)
4 | M6227 | Ferrari 175 Purosangue (SUV) / BY CN | Sheng, Tall boy | 1/8 | 2000 | 2586 | 1443.5 | 1142.5 | WK11(2022) | WK21(2023)
5 | M6210-SC1 | Aston Martin DB5 / BY CN | [John] , Ford | 1/8 | 1800 | 1993.5 | 708.5 | 1285 | WK25(2022) | WK24(2023)
6 | M6210-BES1 | Aston Martin DB5 / BY CN | [John] , Ford | 1/8 | 500 | 260 | 232 | 28 | WK36(2022) | WK07(2023)
7 | M6235 | RB18 F1 2022 Dutch #1 #55 | Cary | 1/8 | 900 | 1064 | 776 | 288 | WK27(2022) | WK2(2023)
8 | M6233 | RR CB03 | Ford, Tall boy | 1/8 | 1400 | 1438.5 | 667 | 771.5 | WK34(2022) | WK24(2023)
9 | M5904 | Ferrari F40 | Tin | 1/18 | 50 | 248 | 78 | 170 | WK40(2022) | WK02(2023)
10 | M0648-SC2 | Maserati 250F (1957 Nurburging) / BY CN | Tin, John | 1/8 | 2000 | 2118.5 | 1600 | 518.5 | WK16(2022) | WK48(2023)
11 | M0648-BES1 | Maserati 250F (1957 Nurburging) / BY CN | Tin, John | 1/8 | 1000 | 826 | 423 | 403 | WK30(2022) | WK45(2023)
12 | M6188 | Mercedes AMG one | Ford | 1/18 | 300 | 656 | 476 | 180 | WK26(2021) | WK11(2023)
13 | M6245 | RedBull RB18 1-4scale Dutch GP | Carry | 1/4 | 600 | 594 | 200 | 394 | WK47(2022) | WK17(2023)
14 | M6241-SC1 | Mercedes F1 W13 2022 1-8 model Brazil #44 | Tall Boy | 1/8 | 100 | 100 | 90 | 10 | WK2(2023) | WK12(2023)
15 | M6241-SC2 | Mercedes F1 W13 2022 1-8 model Brazil #63 | Tall Boy | 1/8 | 650 | 729 | 436 | 293 | WK49(2022) | WK14(2023)
16 | M6195 | Laferrari (close roof) | John | 1/18 | 100 | 100 | 100 | 0 | WK02(2023) | WK23(2023)
17 | M6181-GT3 | Ferrari 296-GT3 | Sheng, John, Ford | 1/8 | 1500 | 2021 | 888.5 | 1132.5 | WK05(2023) | WK32(2023)
18 | M6240 | Aston Martin DB5 / BY CN | Cary | 1/18 | 700 | 392 | 392 | 0 | WK45(2022) | WK45(2023)
19 | M6243 | Bentley Speed 8 sculpture | Tin | 1/43 | 10 | 20 | 20 | 0 | WK07(2023) | WK08(2023) | 外面供应商做的手板
20 | M6264 | Ferrari F1 SF23 Bahrain scale 1-8 | John,Carry | 1/8 | 700 | 929.5 | 692 | 237.5 | WK10(2023) | WK27(2023)
21 | M6276 | Ferrari Daytona SP3 | Tall Boy | 1/18 | 500 | 93 | 93 | 0 | WK08(2023) | WK12(2023) | 画了一半，已转给外面画
22 | M6246 | 250TR scale 1-4 | Ford | 1/4 | 200 | 252 | 252 | 0 | WK09(2023) | WK32(2023)
23 | M6277 | RB19/ RB18 /RB16 SW scale 1-4 | Ford, John | 1/4 | 400 | 88 | 60 | 28 | WK14(2023) | WK20(2023)
24 | M6268-DEV | Ferrari F1 SF23 Bahrain nose 1-12 | Tall boy | 1/12 | 500 | 88 | 68 | 20 | WK17(2023) | WK21(2023)
25 | M6242-DEV | RB19 FSSW scale 1-1 | Ford | 1/1 | 600 | 393 | 172 | 221 | WK11(2023) | WK23(2023)
26 | M6265 | RB19 2023 1:8 model | Sheng, Tall Boy, Cary | 1/8 | 800 | 641.5 | 290 | 351.5 | WK18(2023) | WK28(2023)
27 | M6270-DEV | Ferrari 499P 1:8 | Ford, John, Dylan | 1/8 | 2000 | 2383 | 927 | 1456 | WK17(2023) | WK47(2023)
28 | M6049-SPI-DEV | Ferrari 169S Roma Spider | Tall Boy | 1/8 | 800 | 858 | 204 | 654 | WK23(2023) | WK45(2023)
29 | M6284-DEV | Ferrari 173VS SF90 XX <no open cover> | Sheng | 1/8 | 1200 | 1172.5 | 333 | 839.5 | WK26(2023) | WK48(2023)
30 | M6295 | McLaren 750 coupé | Cary | 1/8 | 200 | 746 | 236 | 510 | WK38(2023) | WK48(2023)
31 | M6284-SPI-DEV | Ferrari 173VSS SF90 XX Spider | Sheng | 1/8 | 500 | 144 | 144 | 0 | WK34(2023) | WK48(2023) | 3D阶段
32 | M5875-BES-18 | Ferrari 333SP | Ping | 1/8 | 800 | 132 | 132 | 0 | WK41(2023) | WK48(2023) | 3D阶段
33 | M6239 | Boeing B-17 | John | 1/32 | 1000 | 440 | 440 | 0 | WK28(2023) | WK48(2023) | 3D阶段
34 | M6279 | Aston Martin F1 AMR23 - Unique Bahrain,Alonso | Tall Boy | 1/5 | 900 | 374 | 374 | 0 | WK35(2023) | WK48(2023) | 3D阶段
35 | M6301 | Aston Martin DBR22 | Sheng,Cary | 1/8 | 1200 | 300 | 300 | 0 | WK41(2023) | WK48(2023) | 3D阶段
36 | M6296 | McLaren Solus GT | Tin,Ping | 1/8 | 1600 | 56 | 56 | 0 | WK45(2023) | WK48(2023) | 3D阶段
37 | M6300 | Ferrari F171 296 Challenge | Ford | 1/8 | 1200 | 104 | 104 | 0 | WK41(2023) | WK48(2023) | 3D阶段
38 | M6297 | McLaren MCL60 F1 | Ford, John | 1/8 | 800 | 144 | 144 | 0 | WK47(2023) | WK48(2023) | 3D阶段
[5 empty] | 32310 | 27037.5 | [5 empty] | 5272.5
改板装板详细统计表
序号 | 项目编码 | 具体事项 | 组别 | Scale | 时间WK) | 时间(h)
1 | M5377-LM | 修装手板+打磨 | 手板 | 1/8 | WK01 | 44
2 | M5541 | 修装手板+打磨 | 手板 | 1/8 | WK01 | 29
3 | M5447 | 修粘手板大件 | 手板 | 1/8 | WK06 | 9
4 | M5448 | 修装手板大件 | 手板 | 1/8 | WK06 | 12
5 | M5377-LM | 修手板 | 手板 | 1/8 | WK06 | 14
6 | M5635 | 修装手板大件 | 手板 | 1/8 | WK07 | 4
7 | M5448 | 修装手板大件 | 手板 | 1/8 | WK07 | 12
8 | M5377-LM | 修手板 | 手板 | 1/8 | WK07 | 27
9 | M5945 | 修装手板大件 | 手板 | 1/8 | WK07 | 4
10 | M5636 | 修装手板大件 | 手板 | 1/8 | WK07 | 4
11 | M5267 | 修装手板大件 | 手板 | 1/8 | WK08 | 2
12 | M5971 | 修装手板大件 | 手板 | 1/8 | WK08 | 3
13 | M5971 | 修装第一套板 | 手板 | 1/8 | WK08 | 3
14 | M5377-LM | 修手板 | 手板 | 1/8 | WK08 | 17
15 | M5248-SEB | 检查旧板改板 | 手板 | 1/8 | WK08 | 32
16 | M5353 | 修装手板大件 | 手板 | 1/8 | WK09 | 2
17 | M5980-R11R12 | 修装手板大件 | 手板 | 1/8 | WK09 | 5
18 | M5980-R11R12 | 拆板 | 手板 | 1/8 | WK09 | 3
19 | M5540 | 检查旧板改板 | 手板 | 1/8 | WK09 | 15
20 | M5248-SEB | 检查旧板改板 | 手板 | 1/8 | WK09 | 3
21 | M6205 | 修装手板大件 | 手板 | 1/8 | WK10 | 4
22 | M6190 | 修装手板大件 | 手板 | 1/8 | WK10 | 2
23 | M5540 | 检查旧板改板 | 手板 | 1/8 | WK10 | 20
24 | M6227 | 装第一套板 | 手板 | 1/8 | WK10 | 97
25 | M6190 | 修装手板大件 | 手板 | 1/8 | WK11 | 10
26 | M5260 | 修装手板大件 | 手板 | 1/8 | WK11 | 3
27 | M5712 | 修装手板大件 | 手板 | 1/8 | WK11 | 3
28 | M6194 | 修装手板大件 | 手板 | 1/8 | WK11 | 3
29 | M6245 | 修装手板大件 | 手板 | 1/8 | WK11 | 9
30 | M5540 | 检查旧板改板 | 手板 | 1/8 | WK11 | 63
31 | M6227 | 装第一套板 | 手板 | 1/8 | WK11 | 25.5
32 | M5377-LM | 帮打磨 | 手板 | 1/8 | WK11 | 2
33 | M6190 | 尺寸管控基准 | 手板 | 1/8 | WK11 | 12
34 | M6215 | 修装手板大件 | 手板 | 1/8 | WK12 | 2
35 | M6003 | 修装第一套板 | 手板 | 1/8 | WK12 | 3
36 | M5540 | 检查旧板改板 | 手板 | 1/8 | WK12 | 50
37 | M6205 | 修成品车 | 手板 | 1/8 | WK12 | 6
38 | M5377-LM | 帮打磨 | 手板 | 1/8 | WK12 | 11
39 | M6190 | 尺寸管控基准 | 手板 | 1/8 | WK12 | 3
40 | M6210 | 帮装第一套板 | 手板 | 1/8 | WK13 | 121.5
41 | M5377-LM | 帮打磨 | 手板 | 1/8 | WK13 | 8
42 | M6210 | 帮装第一套板 | 手板 | 1/8 | WK14 | 102
43 | M0561 | 帮修板 | 手板 | 1/8 | WK14 | 10.5
44 | M0009 | 帮修板 | 手板 | 1/8 | WK14 | 8.5
45 | M6235 | 修装手板大件 | 手板 | 1/8 | WK15 | 2
46 | M6210 | 修装PX-1000大件 | 手板 | 1/8 | WK15 | 6
47 | M5754 | 修装手板大件+打磨 | 手板 | 1/8 | WK15 | 53
48 | M6210 | 帮装第一套板 | 手板 | 1/8 | WK15 | 61
49 | M0561 | 帮修板 | 手板 | 1/8 | WK15 | 2
50 | M0009 | 帮修板 | 手板 | 1/8 | WK15 | 4
51 | M5549 | 帮修板 | 手板 | 1/8 | WK15 | 19
52 | M5539 | 修装手板大件 | 手板 | 1/8 | WK16 | 7
53 | M6210 | 修装PX-1000大件 | 手板 | 1/8 | WK16 | 8
54 | M5754 | 修装手板大件+打磨 | 手板 | 1/8 | WK16 | 3
55 | M6235 | 做基准 | 手板 | 1/8 | WK16 | 18
56 | M5549 | 帮修板 | 手板 | 1/8 | WK16 | 57.5
57 | M6199-CPO | 修装手板大件 | 手板 | 1/8 | WK17 | 5
58 | M6210 | 修装PX-1000大件 | 手板 | 1/8 | WK17 | 18.5
59 | M5377 | 修装手板大件 | 手板 | 1/8 | WK17 | 5
60 | M5945 | 修装手板大件 | 手板 | 1/8 | WK17 | 5
61 | M5248 | 帮修板 | 手板 | 1/8 | WK17 | 10
62 | M5549 | 帮修板 | 手板 | 1/8 | WK17 | 33
63 | M6227 | 装手板大件 | 手板 | 1/8 | WK18 | 10
64 | M6210 | 修PX-1000板 | 手板 | 1/8 | WK18 | 43
65 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK18 | 11
66 | M5356 | 修装手板大件 | 手板 | 1/8 | WK18 | 1.5
67 | M5349 | 修装手板大件 | 手板 | 1/8 | WK18 | 1.5
68 | M6210 | 修装手板大件 | 手板 | 1/8 | WK18 | 1.5
69 | M5356-RL | 帮修板大件 | 手板 | 1/8 | WK18 | 26
70 | M5310 | 帮修板大件 | 手板 | 1/8 | WK18 | 20
71 | M5248-RL | 帮修板大件 | 手板 | 1/8 | WK18 | 31
72 | M5376-RL | 帮修板大件 | 手板 | 1/8 | WK18 | 26
73 | M5344-RL | 帮修板大件 | 手板 | 1/8 | WK18 | 38
74 | M6241 | 装车胎第一套板 | 手板 | 1/8 | WK19 | 4
75 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK19 | 16
76 | M5356-RL | 帮修板大件 | 手板 | 1/8 | WK19 | 67
77 | M5791 | 帮修板大件 | 手板 | 1/8 | WK19 | 32
78 | M5538-RL | 帮修板大件 | 手板 | 1/8 | WK19 | 60
79 | M5376-RL | 帮修板大件 | 手板 | 1/8 | WK19 | 35
80 | M5344-RL | 帮修板大件 | 手板 | 1/8 | WK19 | 10
81 | M5945 | 修装手板大件 | 手板 | 1/8 | WK20 | 4
82 | M00095 | 修装手板大件 | 手板 | 1/8 | WK20 | 3
83 | M5540 | 修装手板大件 | 手板 | 1/8 | WK20 | 7
84 | M0561 | 修装手板大件 | 手板 | 1/8 | WK20 | 2
85 | M5248 | 修装手板大件 | 手板 | 1/8 | WK20 | 4
86 | M5356-RL | 帮修板大件 | 手板 | 1/8 | WK20 | 12
87 | M5791 | 帮修板大件 | 手板 | 1/8 | WK20 | 41
88 | M5538-RL-NRT | 帮修板大件 | 手板 | 1/8 | WK20 | 75
89 | M5974 | 帮修板大件 | 手板 | 1/8 | WK20 | 24
90 | M5248-RL | 帮修板大件 | 手板 | 1/8 | WK20 | 24
91 | M5791 | 帮修板大件 | 手板 | 1/8 | WK21 | 16
92 | M5263 | 帮修板大件 | 手板 | 1/8 | WK21 | 60
93 | M5538-RL-NRT | 帮修板大件 | 手板 | 1/8 | WK21 | 68
94 | M5974 | 帮修板大件 | 手板 | 1/8 | WK21 | 72
95 | M5248-RL | 帮修板大件 | 手板 | 1/8 | WK21 | 20
96 | M5288 | 整理手板 | 手板 | 1/8 | WK22 | 8
97 | M灯箱 | M灯箱 | 手板 | 1/8 | WK22 | 20
98 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK22 | 26
99 | M5249 | 修装手板大件 | 手板 | 1/8 | WK22 | 3
100 | M5739 | 修装手板大件 | 手板 | 1/8 | WK22 | 3
101 | M5757 | 修装手板大件 | 手板 | 1/8 | WK22 | 4
102 | M5278 | 帮修板大件 | 手板 | 1/8 | WK22 | 10
103 | M5263 | 帮修板大件 | 手板 | 1/8 | WK22 | 64
104 | M5538-RL-NRT | 帮修板大件 | 手板 | 1/8 | WK22 | 9.5
105 | M5974 | 帮修板大件 | 手板 | 1/8 | WK22 | 57
106 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK23 | 70.5
107 | M5278 | 帮修板大件 | 手板 | 1/8 | WK23 | 52
108 | M5263 | 帮修板大件 | 手板 | 1/8 | WK23 | 69
109 | M5248-RL | 帮修板打磨-大件 | 手板 | 1/8 | WK23 | 47
110 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK24 | 31
111 | M5224 | 帮修板大件 | 手板 | 1/8 | WK24 | 10
112 | M5263 | 帮修板大件 | 手板 | 1/8 | WK24 | 9
113 | M5248-RL | 帮修板打磨-大件 | 手板 | 1/8 | WK24 | 3
114 | M6242 | 装第一套板 | 手板 | 1/8 | WK24 | 29
115 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK25 | 32
116 | M5542 | 帮修板大件 | 手板 | 1/8 | WK25 | 24
117 | M6210 | 修PX-1000板 | 手板 | 1/8 | WK26 | 7
118 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK26 | 80
119 | M5814 | 修装手板大件 | 手板 | 1/8 | WK26 | 7
120 | M5249 | 修装手板大件 | 手板 | 1/8 | WK26 | 4
121 | M5542 | 帮修板大件 | 手板 | 1/8 | WK26 | 8.5
122 | M6210 | 修PX-1000板 | 手板 | 1/8 | WK27 | 33
123 | M6227 | 修PX-1000板 | 手板 | 1/8 | WK27 | 11
124 | M5376 | 修装手板大件 | 手板 | 1/8 | WK27 | 4
125 | M5971 | 修装手板大件 | 手板 | 1/8 | WK27 | 3
126 | M5542 | 帮修板大件 | 手板 | 1/8 | WK27 | 46
127 | M6210 | 修PX-1000板 | 手板 | 1/8 | WK28 | 24
128 |  | 帮3D装飞机模型 | 手板 |  | WK28 | 42
129 | M6210 | 修PX-1000板 | 手板 | 1/8 | WK29 | 15
130 |  | 帮3D装飞机模型 | 手板 | 1/8 | WK29 | 13
131 | M5376 | 修装手板大件 | 手板 | 1/8 | WK29 | 6
132 | M5356 | 修装手板大件 | 手板 | 1/8 | WK29 | 6
133 | M5712-SPI | 修装手板大件 | 手板 | 1/8 | WK29 | 5
134 | M5538 | 修装手板大件 | 手板 | 1/8 | WK29 | 9
135 | M5248-V5 | 修装手板大件 | 手板 | 1/8 | WK30 | 5
136 | M5791 | 修PX-1000车身-装手板大件 | 手板 | 1/8 | WK30 | 12
137 | M6227 | 修装手板大件 | 手板 | 1/8 | WK30 | 12
138 | M5538 | 修装手板大件 | 手板 | 1/8 | WK30 | 9
139 | M5791 | 修PX-1000车身-装手板大件 | 手板 | 1/8 | WK31 | 8
140 | M5469 | 修装手板大件 | 手板 | 1/8 | WK31 | 7
141 | M5768 | 修装手板大件 | 手板 | 1/8 | WK31 | 3
142 | M5288-D70 | 修装手板大件 | 手板 | 1/8 | WK32 | 6
143 | M5288-L70 | 修装手板大件 | 手板 | 1/8 | WK32 | 5
144 | M5288-L71 | 修装手板大件 | 手板 | 1/8 | WK32 | 6
145 | M5344 | 修装手板大件 | 手板 | 1/8 | WK32 | 5
146 | M5264 | 修装手板大件 | 手板 | 1/8 | WK32 | 5
147 | M6003 | 修装手板大件 | 手板 | 1/8 | WK34 | 4
148 | M5249 | 修装手板大件 | 手板 | 1/8 | WK34 | 6
149 | M6181-GT3 | 修PX-1000板 | 手板 | 1/8 | WK35 | 10
150 | M6181-GT3 | 修PX-1000板 | 手板 | 1/8 | WK36 | 48
151 | M5263 | 修装手板大件 | 手板 | 1/8 | WK36 | 6
152 | M5740 | 修装手板大件 | 手板 | 1/8 | WK36 | 16
153 | M6181-GT3 | 修PX-1000板 | 手板 | 1/8 | WK37 | 54
154 | M6181-GT3 | 修PX-1000板 | 手板 | 1/8 | WK38 | 4
155 | M6199 | 修装手板大件 | 手板 | 1/8 | WK38 | 6
156 | M5730 | 修装手板大件 | 手板 | 1/8 | WK39 | 5
157 | M6049 | 修装手板大件 | 手板 | 1/8 | WK39 | 5
158 | M5539 | 修装手板大件 | 手板 | 1/8 | WK39 | 11
159 | M6210 | 修装手板大件 | 手板 | 1/8 | WK39 | 6
160 | M6181-GT3 | 修装手板大件 | 手板 | 1/8 | WK40 | 7
161 | M5875 | 修装手板大件 | 手板 | 1/8 | WK40 | 6.5
162 | M5503 | 修装手板大件 | 手板 | 1/8 | WK41 | 18
163 | M5540 | 修装手板大件 | 手板 | 1/8 | WK41 | 2
164 | M5971 | 修装手板大件 | 手板 | 1/8 | WK41 | 4
165 | M6265 | 修装手板大件 | 手板 | 1/8 | WK41 | 1
166 | M5875 | 修装手板大件 | 手板 | 1/8 | WK41 | 3
167 | M5712 | 修装手板大件 | 手板 | 1/8 | WK42 | 10.5
168 | M5248-V9 | 修装手板大件 | 手板 | 1/8 | WK42 | 16
169 | M5377-LM-ERO | 修装手板大件 | 手板 | 1/8 | WK42 | 24
170 | M6270 | 修PX-1000板 | 手板 | 1/8 | WK44 | 13
171 | M6270 | 装第一套板 | 手板 | 1/8 | WK44 | 138
172 | M6205-SC3 | 装第一套板 | 手板 | 1/8 | WK44 | 29
173 | M5448 | 帮修板大件 | 手板 | 1/8 | WK44 | 26
174 | M5248-V9 | 修装手板大件 | 手板 | 1/8 | WK45 | 6
175 | M5945 | 修装手板大件 | 手板 | 1/8 | WK45 | 5
176 | M5945-MVS | 修装手板大件 | 手板 | 1/8 | WK45 | 5
177 | M5945-GTB | 修装手板大件 | 手板 | 1/8 | WK45 | 5
178 | M6270 | 装第一套板 | 手板 | 1/8 | WK45 | 9
179 | M5756 | 修装手板大件 | 手板 | 1/8 | WK45 | 5
180 | M5751 | 修装手板大件 | 手板 | 1/8 | WK45 | 5
181 | M6190 | 修装手板大件 | 手板 | 1/8 | WK45 | 6
182 | M5798 | 帮修板大件 | 手板 | 1/8 | WK46 | 25
183 | M6270 | 修PX-1000板 | 手板 | 1/8 | WK46 | 43.043
184 | M5448 | 帮修板大件 | 手板 | 1/8 | WK46 | 63
185 | M5712 | 修装板大件 | 手板 | 1/8 | WK46 | 1
186 | M6270 | 修PX-1000板 | 手板 | 1/8 | WK47 | 92
187 | M5887 | 修装板大件 | 手板 | 1/8 | WK47 | 5
188 | M5501 | 装第一套板烂板 | 手板 | 1/8 | WK47 | 2
189 | M5448 | 帮修板大件 | 手板 | 1/8 | WK47 | 4
190 | M5503 | 修装板大件 | 手板 | 1/8 | WK47 | 2
191 | M6196-GTS | 装第一套板 | 手板 | 1/8 | WK48 | 53
192 | M6270 | 修PX-1000板 | 手板 | 1/8 | WK48 | 100
193 | M5541 | 修装板大件 | 手板 | 1/8 | WK48 | 4
194 | M5712-SPI | 修装手板 | 手板 | 1/8 | WK48 | 12
195 | M6049 | 修装手板大件 | 手板 | 1/8 | WK48 | 4
196 | M5914 | 修装手板大件 | 手板 | 1/8 | WK48 | 3