## Kpi
TEAM | T# | Task Description | Judge | Unit | GOOD | <<< | AVERAGE | >>> | BAD | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2D Team | T1 | On Time Delivery (Days of Delay) | Engineer | Day | < -7 | 0 < … < -7 | 0 | 0 > … > 7 | > 7 | FEB: 5; MAR: 3; APR: 5; MAY: <Need to arrange OT Work / recruitement / meeting HR+2D
| T2 | Task Error, Number of Mistakes | Engineer | Count | 0 | 0 > … > 5 | 5 | 5 > … > 10 | > 10 | FEB: 3; MAR: 3; APR: 2; MAY: <Quality OK
| T3 | Task allocated to Kevin | Matt | Hour | 40 | 30 | 20 | 10 | 0 | FEB: 0; MAR: 10; APR: 0; MAY: <Can't be done in easy way
3D Team | T1 | On Time Delivery (Weeks of Delay) | Matt / DRF | Week | < -2 | 0 < … < -2 | 0 | 0 > … > 3 | > 3 | FEB: 2; MAR: 0; APR: 2; MAY: <Due to CoVid and Cust info delay, better daily
| T2 | Effort Allocated Respect (Hours of Delay) | Matt / DRF | Hour | < -50 | 0 < … < -50 | 0 | 0 > … > 200 | > 200 | FEB: 100; MAR: 0; APR: 100; MAY: <Need some staff being more autonomous / meeting done in this way / load adjusted
| T3 | Number of mistakes | Matt | Count | 0 | 0 > … > 5 | 5 | 5 > … > 10 | > 10 | FEB: 3; MAR: 2; APR: 4; MAY: <Good BUT still some stupid mistake, 3D mistake = money, May, ajust target to be more rude
Photo | T1 | 2D Task On time (% achieved good and On time) | Youli | % | 100 | 75 | 50 | 25 | 0 | FEB: 0; MAR: 75; APR: 0; MAY: <Too limited capacity, no work given
| T2 | Proactive to enhance Technics | Matt | Count | < 3 | 3 | 2 | 1 | 0 | FEB: 2; MAR: 2; APR: 2; MAY: <Very open to check Marketing for UK, not for Internal 2D, need UK returns
PECS | T1 | Parts on Time (Weeks of Delay) | PECS | Weeks | 0 | 0 > … > 0,5 | 0,5 > … > 1 | 1 > … > 2 | > 2 | FEB: 0; MAR: 1; APR: 0; MAY: <Good and smooth
| T2 | Number of Mistaken / damaged Shipments | PECS | Count | 0 | 0 > … > 5 | 5 | 5 > … > 10 | > 10 | FEB: 7; MAR: 3; APR: 4; MAY: <Some misunderstanding and not clear instr. from PEcs
| T3 | Number of Other Task Late or missed | Matt | Count | 0 | 0 > … > 5 | 5 | 5 > … > 10 | > 10 | FEB: 3; MAR: 0; APR: 0; MAY: <Perfect last month, good reactivity with Brisotl projects
PROTOTYPE | T1 | On Time Delivery (Weeks of Delay) | Matt / DRF | Week | < -2 | 0 < … < -2 | 0 | 0 > … > 3 | > 3 | FEB: 0; MAR: 0; APR: 3; MAY: <Information/confirmation delay due to CoVid, Better now, but lot of complexe bespokes
| T2 | Post Meeting Improvement On Time (weeks of Delay) | Matt / DRF | Week | < -2 | 0 < … < -2 | 0 | 0 > … > 3 | > 3 | FEB: 1; MAR: 0; APR: 2; MAY: <Massing load of ECR to threat, Focus on RR projects, other got delay
| T3 | ECN post Sample Updates on Time (Weeks of Delays) | Matt / DRF | Week | < -2 | 0 < … < -2 | 0 | 0 > … > 3 | > 3 | FEB: -1; MAR: 1; APR: 0; MAY: <On Time but really need better comment during prototype Check
| T4 | ECN post Batch 1 counter | Engineer | Count | 0 | 1 | 2 | 3 | > 3 | FEB: 2; MAR: 0; APR: 5; MAY: <Mainly Assembly issues on M6108 and M5980, need consider orders and Deeper check proto
[5 empty] | 100% | 75% | 50% | 25% | 0
OK, IF TIME, CHECK TO IMPROVE WITH ACTORS
ENSURE TO CONTROL NO WORST THAN NOW
NEED TAKE ACTION IMMEDIATELY
KPI Bonus Calculator | [9 empty] | FEB: JANUARY; JUL: FEBRUARY; DEC: MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
Name |  | Title | [7 empty] | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT | T1 | T2 | T3 | T4 | ToT
Youli |  | 2D designer | [7 empty] | JUL: 25; AUG: 75; SEP: 0; OCT: X; NOV: 33.3333; DEC: 25 | 75 | 25 | X | 41.6667
Yuma |  | 2D Designer | [7 empty] | JUL: 25; AUG: 75; SEP: X; OCT: X; NOV: 50; DEC: 25 | 75 | X | X | 50
Tin |  | 3D designer | [7 empty] | JUL: 75; AUG: 100; SEP: 75; OCT: X; NOV: 83.3333; DEC: 75 | 100 | 75 | X | 83.3333
Fei |  | 3D designer | [7 empty] | JUL: 25; AUG: 50; SEP: 25; OCT: X; NOV: 33.3333; DEC: 50 | 75 | 50 | X | 58.3333
Ford |  | 3D designer | [7 empty] | JUL: 75; AUG: 100; SEP: 75; OCT: X; NOV: 83.3333; DEC: 75 | 100 | 75 | X | 83.3333
TallBoy |  | 3D designer | [7 empty] | JUL: 50; AUG: 75; SEP: 50; OCT: X; NOV: 58.3333; DEC: 75 | 75 | 75 | X | 75
Cary |  | 3D designer | [7 empty] | JUL: 25; AUG: 50; SEP: 50; OCT: X; NOV: 41.6667; DEC: 75 | 50 | 75 | X | 66.6667
Kevin |  | PhotoGrapher and 2D Helper | [7 empty] | JUL: 0; AUG: 50; SEP: X; OCT: X; NOV: 25 |  |  | X | 0
April |  | Development Assistant | [7 empty] | JUL: 100; AUG: 50; SEP: 75; OCT: X; NOV: 75 |  |  | X | 0
Jimmy |  | Prototype Supervizor | [7 empty] | JUL: 100; AUG: 25; SEP: 75; OCT: 50; NOV: 62.5 |  |  |  | 0
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2020 03 30 - Manpower arrangement - Need to be solved with AMY
Note on N14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2020 03 30 - Due to Casting Capacity M6041 - Due to Project def. M6026
Note on N20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2020 03 30 - Priorities build delay

## Schedule
|  |  |  | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03
STANDARD | Sku | Scale | DU | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5
Ferrari F1-89 1:18 car | M6308 | 1/18 | 0 | bar: 2024-06-24 to 2024-07-15
Ferrari 499P 1:1 steering wheel | M6314 | 1/1 | 2.7273 | bar: 2024-06-10 to 2024-07-08
McLaren Solus GT | M6296 | 1/8 | 7.2727 | bar: 2024-06-10 to 2024-06-24; 2024-07-08 to 2024-07-15; 2024-08-12 to 2024-09-23
Ferrari F167 Spider--12 Cilindri Spider | M6298-SPI | 1/8 | 2.7273 | bar: 2024-06-10 to 2024-06-24; 2024-07-08 to 2024-07-22; 2024-08-05 to 2024-09-16
Boeing B-17 | M6239 | 1/32 | 4.5455 | bar: 2024-06-17 to 2024-08-05
499P 1:5 car | M6315 | 1/5 | bar: 2024-06-17 to 2024-06-24; 2024-07-08 to 2024-07-15; 2024-07-29 to 2024-09-23
Maserati 250F 1:18 car | M6304 | 1/18 | 1.8182 | bar: 2024-07-15 to 2024-08-26
Bentley Blower 1:18 car | M6307 | 1/18 | 4.5455 | bar: 2024-07-22 to 2024-09-09
Aston Martin Valkyrie 1:8 | M6302 | 1/8 | 7.2727 | bar: 2024-06-10; 2024-06-24 to 2024-07-08; 2024-07-22 to 2024-08-12; 2024-08-26 to 2024-10-21
Lamborghini Revuelto | M6299 | 1/8 | 6.8182 | bar: 2024-06-10 to 2024-06-17; 2024-07-01 to 2024-07-08; 2024-07-22 to 2024-07-29; 2024-08-12 to 2024-09-30
McLaren P18 | M6xxx | 1/8 | 7.2727 | bar: 2024-06-10 to 2024-07-22; 2024-08-05 to 2024-08-12; 2024-08-26 to 2024-09-09; 2024-09-23 to 2024-10-07; 2024-11-04 to 2024-12-30
Bugatti Engine sculpt | M6xxx | 1/6 | bar: 2024-06-17 to 2024-07-08; 2024-08-12 to 2024-10-07
Mercedes Uhlenhaut 1:8 car | M6263 | 1/8 | 13.6364 | bar: 2024-06-10 to 2024-08-12; 2024-08-26 to 2024-09-09; 2024-09-23 to 2024-09-30; 2024-10-21 to 2024-12-23
McLaren 765LT | M6244-SPI-BES1 | 1/8 | 0.90909 | bar: 2024-06-24 to 2024-07-29
Falcon Bristol | M6248 | bar: 2024-06-10 to 2024-08-19
Ferrari F171 296 Challenge | M6300 | 1/8 | 5.4545 | bar: 2024-06-24 to 2024-07-08; 2024-07-22 to 2024-07-29; 2024-08-12 to 2024-08-26; 2024-09-09; 2024-09-30 to 2024-11-04
McLaren MCL38 | bar: 2024-06-10 to 2024-07-08; 2024-07-22 to 2024-07-29; 2024-08-12 to 2024-08-26; 2024-09-09 to 2024-09-16; 2024-10-07 to 2024-12-02
Mercedes Uhlenhaut 1:18 car | M6309 | 1/18 | 1.8182 | bar: 2024-07-08; 2024-09-09; 2024-10-07; 2024-10-21 to 2024-12-09
McLaren P18 1-18 | M6xxx | 1/18 | 0 | bar: 2024-07-08 to 2024-08-26; 2024-09-09; 2024-10-07; 2024-10-21 to 2024-12-09
Range Rover | bar: 2024-07-08 to 2024-08-05; 2024-08-19 to 2024-08-26; 2024-09-09 to 2024-09-23; 2024-10-07 to 2024-10-14; 2024-11-04 to 2024-12-23
Ferrari 499P 2024 1:8 car | M6xxx | 1/8 | 1.3636 | bar: 2024-07-22 to 2024-08-05; 2024-08-19 to 2024-09-02; 2024-09-16 to 2024-09-23; 2024-10-14 to 2024-12-09
Ferrari 499P 2024 1:18 car | M6xxx | 1/18 | 1.3636 | bar: 2024-08-05 to 2024-08-12
Hennessy | bar: 2024-07-08 to 2024-08-05; 2024-08-19 to 2024-08-26; 2024-09-09 to 2024-09-23; 2024-10-07 to 2024-10-14; 2024-11-04 to 2024-12-23
[18 empty] | 3D 3weeks offset | [6 empty] | Prototype 3 weeks offset | [10 empty] | Sample 3 weeks offset
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Development Unit
Note on B9: Hennessy/Pininfarina/charge/Alfa Romeo
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Basic : McLaren 720